## CTR
CTR FORM – COST, TIME & RESOURCE
Commercial-style planning document for the NIT Bank Linux Process Operations Lab.
1. Project Information
Project | NEXUS Ventures Linux Process Operations Lab | Contract No. | TRAINING-2026 | Work Order | LPX-001 | Revision | 01
Contractor | Nexus Institute of Technology | Customer | NIT Bank Training Division | Status | For Training Approval | Date | 2026-07-21
Planned Start | 2026-07-27 | Planned Finish | 2026-08-14 | Duration | 15 Working Days | Working Hours | 105 Hours
CTR / Activity No. | HS-100 | Title | Linux Process Operations Project | Prepared By | Project Controls | Checked By | Instructor
Business Objective | Train students to deliver a controlled Linux process-management change using business documentation, technical implementation, testing, incident recovery and formal acceptance.
2. Activity Description
1 | Create the project charter, CTR, PMP, NCD, ITQ register and master schedule.
2 | Confirm student roster, VM inventory, root access, repositories and rollback snapshots.
3 | Create long-running, CPU-intensive, parent-child and zombie process demonstrations.
4 | Test foreground/background jobs, signals, priorities, nohup and /proc.
5 | Create a dedicated service account and systemd-managed report-generator service.
6 | Simulate a bank operations incident involving high CPU and service interruption.
7 | Execute validation tests, capture evidence and restore the service.
8 | Complete the incident report, business acceptance and lessons learned.
3. Input Requirements / Customer Prerequisites
I01 | One assigned Rocky Linux 9 VM per student in Xen Orchestra.
I02 | Direct root account access limited to the assigned training VM.
I03 | Working Rocky repositories and permission to install procps-ng, psmisc, gcc and tree.
I04 | Xen Orchestra console access or lab-administrator support for recovery.
I05 | Approved pre-change snapshot and evidence-storage location.
I06 | Student roster, VM naming convention and project working hours.
I07 | Approval to use a synthetic bank scenario with no real customer or production data.
I08 | Instructor availability for Go/No-Go, incident simulation and acceptance.
4. Outputs / Deliverables
D01 | Approved CTR, PMP, NCD, ITQ Register and Master Schedule.
D02 | Linux Process Functional Design Specification and student implementation guide.
D03 | Working process-lab scripts and systemd service on each student VM.
D04 | Completed validation evidence and automated validation result.
D05 | Bank-style incident report showing root cause, corrective actions and recovery.
D06 | Student presentation, lessons learned and project closure approval.
5. Cost, Time and Resource Estimate
Resource / Role | Qty | Planned Hours | Hourly Rate (USD) | Labour Cost | Other Cost | Total Cost | Notes
Project Manager / Instructor | 1 | 18 | 50 | 900 | 0 | 900 | Scope, approvals, schedule, reviews and closure.
Linux Technical Lead | 1 | 36 | 55 | 1980 | 0 | 1980 | FDS, technical coaching, troubleshooting and acceptance.
Xen Orchestra / Lab Administrator | 1 | 18 | 45 | 810 | 0 | 810 | VM allocation, snapshots and recovery support.
Business Analyst / Document Controller | 1 | 12 | 40 | 480 | 0 | 480 | CTR, ITQ, revisions, evidence and final pack.
Student Team (training hours) | 1 | 105 | 0 | 0 | 0 | 0 | Tracked as learning effort; not externally billed.
Software / Licensing | 1 | 0 | 0 | 0 | 0 | 0 | Rocky Linux and project tools are open source/existing.
Contingency | 1 | 0 | 0 |  | 417 | 417 | 10% of paid labour cost.
TOTAL ESTIMATED PROJECT COST |  |  |  | 4170 | 417 | 4587
6. Notes, Assumptions and Exclusions
A01 | The project is a classroom simulation and must not use real bank customer data, production credentials or production systems.
A02 | Every student works only on the assigned Xen Orchestra VM and is responsible for recording the VM hostname and IP.
A03 | Students temporarily use direct root accounts for the learning environment; production environments should use named accounts and least privilege.
A04 | The baseline assumes one Rocky Linux 9 VM per student, 1 vCPU, 1 GB RAM and 20 GB disk.
A05 | Schedule begins only after VM access, repositories, snapshots and evidence storage are available.
A06 | Actual classroom cost depends on instructor rates, class size and lab infrastructure already owned by the institute.
A07 | High availability, real banking application integration, 24x7 support and external monitoring are excluded.
A08 | Acceptance requires successful technical validation, incident recovery, evidence submission and instructor sign-off.
7. Approval
Prepared By |  | Role | Business Analyst / Document Controller | Date |  | Signature
Reviewed By |  | Role | Linux Technical Lead | Date |  | Signature
Approved By |  | Role | Project Manager / Instructor | Date |  | Signature
Business Acceptance |  | Role | NIT Bank Training Sponsor | Date |  | Signature