## Interface Technical Query
INTERFACE REGISTER – TECHNICAL / BUSINESS QUERY (ITQ)
Open questions, customer inputs, ownership and closure evidence for the Linux Process Operations Lab.
TQ Number | Created On | Initiator | Responsible Person | Due Date | Reference Document | Document Description | Action / Information Requested | Initial Requirement Confirmed | Response / Reference | Cost or Schedule Impact | Business Value / Risk | Status
1 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Capacity / roster | Confirm final student count and the number of Rocky Linux VMs required. | No |  | To Be Assessed | Class size affects VM capacity, evidence volume and instructor workload. | OPEN
2 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Asset assignment | Provide the approved student-to-VM assignment list including hostname and IP address. | No |  | To Be Assessed | Prevents students from changing the wrong system. | OPEN
3 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Access management | Confirm that every assigned VM has a working root account and that credentials will be distributed securely. | No |  | To Be Assessed | Missing access blocks the technical work. | OPEN
4 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Infrastructure sizing | Confirm the minimum VM specification: vCPU, RAM and disk. | No |  | To Be Assessed | Insufficient resources may cause false performance incidents. | OPEN
5 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Software prerequisite | Confirm Rocky Linux version and repository access for procps-ng, psmisc, gcc and tree. | No |  | To Be Assessed | Required commands and compiler may be unavailable. | OPEN
6 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Recovery interface | Identify the Xen Orchestra administrator responsible for snapshots, console access and VM recovery. | No |  | To Be Assessed | Rollback may be delayed without an available administrator. | OPEN
7 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Change control | Approve the snapshot naming convention and retention period for classroom snapshots. | No |  | To Be Assessed | Uncontrolled snapshots consume storage and create confusion. | OPEN
8 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Schedule baseline | Confirm the project start date, daily working hours and final acceptance date. | No |  | To Be Assessed | Required for the master schedule and student deadlines. | OPEN
9 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Document control | Confirm the evidence repository and naming convention for screenshots, command output and incident reports. | No |  | To Be Assessed | Evidence may be lost or cannot be traced to a student. | OPEN
10 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Resource organization | Confirm whether students work individually or in teams and identify team leads. | No |  | To Be Assessed | Changes responsibility and grading accountability. | OPEN
11 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Privacy / compliance | Approve the synthetic bank scenario and confirm that no real customer, account or transaction data will be used. | No |  | To Be Assessed | Prevents data-protection and confidentiality issues. | OPEN
12 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Governance | Confirm who acts as Project Sponsor, Project Manager, Linux Technical Lead and Business Approver. | No |  | To Be Assessed | Formal decisions and acceptance need named owners. | OPEN
13 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Change approval | Approve the Go / No-Go criteria before technical implementation. | No |  | To Be Assessed | Students must understand that incomplete prerequisites stop a change. | OPEN
14 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Rollback strategy | Approve the rollback triggers and whether snapshot revert or manual cleanup is the preferred method. | No |  | To Be Assessed | Reduces recovery time and protects the shared lab. | OPEN
15 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Security design | Confirm the expected service account name and least-privilege requirement for the systemd service. | No |  | To Be Assessed | Demonstrates separation between administration and service execution. | OPEN
16 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Scope control | Confirm whether Cockpit or other optional monitoring interfaces are allowed; the core project does not require them. | No |  | To Be Assessed | Avoids unnecessary software and open ports. | OPEN
17 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Quality / acceptance | Confirm the grading acceptance criteria and required pass mark for technical validation. | No |  | To Be Assessed | Students need measurable completion criteria. | OPEN
18 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Operational safety | Confirm the maximum time allowed for the high-CPU fault simulation. | No |  | To Be Assessed | Prevents excessive shared-host resource consumption. | OPEN
19 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Incident escalation | Confirm the process for reporting an unexpected VM failure or damage to another student's environment. | No |  | To Be Assessed | Ensures rapid containment and accountability. | OPEN
20 | 2026-07-21 | Project Controls | TBD | 2026-07-26 | CTR / PMP / NCD | Deliverable control | Confirm the final deliverable list: CTR, PMP, NCD, ITQ, Schedule, FDS, validation evidence, incident report and presentation. | No |  | To Be Assessed | Prevents scope dispute and missing business documents. | OPEN

## ITQ Summary
ITQ Summary and Decision Dashboard
Management view of open business and technical decisions.
Metric | Value | Target | Interpretation | Decision Category | Owner | Required Before
Total Queries | 20 | 20 | All required inputs identified | Class Size / VM Capacity | Project Manager / Lab Admin | Schedule Baseline
Open Queries | 20 | 0 | Must be closed or accepted before Go / No-Go | Root Access / Credentials | Lab Administrator | Go / No-Go
Closed Queries | 0 | 20 | Evidence/reference must be recorded | Snapshot / Rollback | Lab Administrator | Go / No-Go
High-Impact Queries | 0 | 0 | Escalate to Project Sponsor / PM | Evidence / Document Control | Document Controller | Implementation
|  |  |  | Privacy / Synthetic Data | Business Owner | Project Approval
|  |  |  | Acceptance / Grading | Instructor | Validation
|  |  |  | Final Deliverables | Project Manager | Project Closure