## Master Schedule
NIT Bank Linux Process Operations Lab – Baseline Master Schedule
15-working-day classroom project using a business project-control lifecycle.
WBS | Activity Name | Type | Owner | Duration (Workdays) | Start | Finish | Predecessor / Dependency | Deliverable | Status
1.0 | Project Initiation & Controls | Phase | Project Manager | 2 | 2026-07-27 | 2026-07-28 |  | PMP / CTR / NCD approvals | Not Started
1.1 | Confirm business objective and project sponsor | Task | Project Manager | 1 | 2026-07-27 | 2026-07-27 |  | Approved objective | Not Started
1.2 | Issue CTR – Cost, Time and Resource document | Task | Project Manager | 1 | 2026-07-27 | 2026-07-27 |  | CTR REV01 | Not Started
1.3 | Issue PMP and project organization | Task | Project Manager | 1 | 2026-07-27 | 2026-07-27 |  | PMP REV01 | Not Started
1.4 | Issue NCD and rollback plan | Task | Linux Lead | 1 | 2026-07-28 | 2026-07-28 |  | NCD REV01 | Not Started
1.5 | Issue ITQ register and close critical queries | Task | Project Manager | 1 | 2026-07-28 | 2026-07-28 |  | ITQ Register | Not Started
2.0 | Design & Readiness | Phase | Linux Lead | 3 | 2026-07-29 | 2026-07-31 |  | Approved design and ready VMs | Not Started
2.1 | Complete VM inventory and student assignments | Task | Lab Administrator | 1 | 2026-07-29 | 2026-07-29 |  | Inventory | Not Started
2.2 | Confirm root access, repositories and packages | Task | Student Team | 1 | 2026-07-29 | 2026-07-29 |  | Readiness evidence | Not Started
2.3 | Create Xen Orchestra pre-change snapshots | Task | Lab Administrator | 1 | 2026-07-30 | 2026-07-30 |  | Snapshot IDs | Not Started
2.4 | Review FDS, acceptance criteria and evidence rules | Task | Instructor | 1 | 2026-07-30 | 2026-07-30 |  | Design review | Not Started
2.5 | Go / No-Go review | Milestone | Project Manager | 0 | 2026-07-31 | 2026-07-31 |  | GO approval | Not Started
3.0 | Technical Build | Phase | Student Team | 4 | 2026-08-01 | 2026-08-04 |  | Working process lab | Not Started
3.1 | Create report-generator and job-control exercises | Task | Student Team | 1 | 2026-08-01 | 2026-08-01 |  | Scripts and evidence | Not Started
3.2 | Complete signal-management tests | Task | Student Team | 1 | 2026-08-02 | 2026-08-02 |  | Signal test evidence | Not Started
3.3 | Create CPU worker and priority tests | Task | Student Team | 1 | 2026-08-02 | 2026-08-02 |  | CPU / nice evidence | Not Started
3.4 | Complete nohup and /proc exercises | Task | Student Team | 1 | 2026-08-03 | 2026-08-03 |  | Persistence evidence | Not Started
3.5 | Create parent-child and zombie demonstrations | Task | Student Team | 1 | 2026-08-03 | 2026-08-03 |  | Process-tree evidence | Not Started
3.6 | Create reportsvc and systemd service | Task | Student Team | 1 | 2026-08-04 | 2026-08-04 |  | Active service | Not Started
4.0 | Testing & Incident Simulation | Phase | Linux Lead | 3 | 2026-08-05 | 2026-08-07 |  | Validated recovery | Not Started
4.1 | Execute automated validation tests | Task | Student Team | 1 | 2026-08-05 | 2026-08-05 |  | Validation log | Not Started
4.2 | Run high-CPU bank incident scenario | Task | Instructor / Students | 1 | 2026-08-06 | 2026-08-06 |  | Incident evidence | Not Started
4.3 | Restore service and confirm business acceptance | Task | Student Team | 1 | 2026-08-07 | 2026-08-07 |  | Recovery evidence | Not Started
4.4 | Technical acceptance review | Milestone | Linux Lead | 0 | 2026-08-07 | 2026-08-07 |  | Technical sign-off | Not Started
5.0 | Handover & Closure | Phase | Project Manager | 3 | 2026-08-08 | 2026-08-10 |  | Closed project | Not Started
5.1 | Complete incident report and lessons learned | Task | Student Team | 1 | 2026-08-08 | 2026-08-08 |  | Incident report | Not Started
5.2 | Update final documents and evidence register | Task | Document Controller | 1 | 2026-08-09 | 2026-08-09 |  | As-built pack | Not Started
5.3 | Knowledge-transfer presentation | Task | Student Team | 1 | 2026-08-10 | 2026-08-10 |  | Presentation | Not Started
5.4 | Business acceptance and project closure | Milestone | Business Owner | 0 | 2026-08-10 | 2026-08-10 |  | Closure approval | Not Started

## Progress Tracker
Project Progress and Delivery Tracker
Use weekly status reviews to monitor schedule, hours, deliverables and corrective actions. | [13 empty] | Project KPI Summary
[14 empty] | KPI | Value | Target | Status
WBS | Task | Owner | Planned Start | Planned Finish | Planned Hours | Actual Hours | % Complete | Schedule Status | Deliverable | Evidence Ref | Issue / Blocker | Corrective Action | Next Review | Planned Tasks | 24 | 24 | Baseline
1.1 | Confirm business objective and project sponsor | Project Manager | 2026-07-27 | 2026-07-27 | 7 | 0 | 0% | Not Started | Approved objective |  |  |  | 2026-07-29 | Completed Tasks | 0 | 24 | Pending
1.2 | Issue CTR – Cost, Time and Resource document | Project Manager | 2026-07-27 | 2026-07-27 | 7 | 0 | 0% | Not Started | CTR REV01 |  |  |  | 2026-07-29 | Planned Hours | 147 | 147 | Baseline
1.3 | Issue PMP and project organization | Project Manager | 2026-07-27 | 2026-07-27 | 7 | 0 | 0% | Not Started | PMP REV01 |  |  |  | 2026-07-29 | Actual Hours | 0 | 147 | Pending
1.4 | Issue NCD and rollback plan | Linux Lead | 2026-07-28 | 2026-07-28 | 7 | 0 | 0% | Not Started | NCD REV01 |  |  |  | 2026-07-30
1.5 | Issue ITQ register and close critical queries | Project Manager | 2026-07-28 | 2026-07-28 | 7 | 0 | 0% | Not Started | ITQ Register |  |  |  | 2026-07-30
2.1 | Complete VM inventory and student assignments | Lab Administrator | 2026-07-29 | 2026-07-29 | 7 | 0 | 0% | Not Started | Inventory |  |  |  | 2026-07-31
2.2 | Confirm root access, repositories and packages | Student Team | 2026-07-29 | 2026-07-29 | 7 | 0 | 0% | Not Started | Readiness evidence |  |  |  | 2026-07-31
2.3 | Create Xen Orchestra pre-change snapshots | Lab Administrator | 2026-07-30 | 2026-07-30 | 7 | 0 | 0% | Not Started | Snapshot IDs |  |  |  | 2026-08-01
2.4 | Review FDS, acceptance criteria and evidence rules | Instructor | 2026-07-30 | 2026-07-30 | 7 | 0 | 0% | Not Started | Design review |  |  |  | 2026-08-01
2.5 | Go / No-Go review | Project Manager | 2026-07-31 | 2026-07-31 | 0 | 0 | 0% | Not Started | GO approval |  |  |  | 2026-08-02
3.1 | Create report-generator and job-control exercises | Student Team | 2026-08-01 | 2026-08-01 | 7 | 0 | 0% | Not Started | Scripts and evidence |  |  |  | 2026-08-03
3.2 | Complete signal-management tests | Student Team | 2026-08-02 | 2026-08-02 | 7 | 0 | 0% | Not Started | Signal test evidence |  |  |  | 2026-08-04
3.3 | Create CPU worker and priority tests | Student Team | 2026-08-02 | 2026-08-02 | 7 | 0 | 0% | Not Started | CPU / nice evidence |  |  |  | 2026-08-04
3.4 | Complete nohup and /proc exercises | Student Team | 2026-08-03 | 2026-08-03 | 7 | 0 | 0% | Not Started | Persistence evidence |  |  |  | 2026-08-05
3.5 | Create parent-child and zombie demonstrations | Student Team | 2026-08-03 | 2026-08-03 | 7 | 0 | 0% | Not Started | Process-tree evidence |  |  |  | 2026-08-05
3.6 | Create reportsvc and systemd service | Student Team | 2026-08-04 | 2026-08-04 | 7 | 0 | 0% | Not Started | Active service |  |  |  | 2026-08-06
4.1 | Execute automated validation tests | Student Team | 2026-08-05 | 2026-08-05 | 7 | 0 | 0% | Not Started | Validation log |  |  |  | 2026-08-07
4.2 | Run high-CPU bank incident scenario | Instructor / Students | 2026-08-06 | 2026-08-06 | 7 | 0 | 0% | Not Started | Incident evidence |  |  |  | 2026-08-08
4.3 | Restore service and confirm business acceptance | Student Team | 2026-08-07 | 2026-08-07 | 7 | 0 | 0% | Not Started | Recovery evidence |  |  |  | 2026-08-09
4.4 | Technical acceptance review | Linux Lead | 2026-08-07 | 2026-08-07 | 0 | 0 | 0% | Not Started | Technical sign-off |  |  |  | 2026-08-09
5.1 | Complete incident report and lessons learned | Student Team | 2026-08-08 | 2026-08-08 | 7 | 0 | 0% | Not Started | Incident report |  |  |  | 2026-08-10
5.2 | Update final documents and evidence register | Document Controller | 2026-08-09 | 2026-08-09 | 7 | 0 | 0% | Not Started | As-built pack |  |  |  | 2026-08-10
5.3 | Knowledge-transfer presentation | Student Team | 2026-08-10 | 2026-08-10 | 7 | 0 | 0% | Not Started | Presentation |  |  |  | 2026-08-10
5.4 | Business acceptance and project closure | Business Owner | 2026-08-10 | 2026-08-10 | 0 | 0 | 0% | Not Started | Closure approval |  |  |  | 2026-08-10

## Gantt Chart
15-Day Project Gantt Chart
A visual schedule linking business controls, technical build, testing and project closure.
[7 empty] | Jul | Jul | Jul | Jul | Jul | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug | Aug
WBS | Activity | Owner | Type | Start | Finish | Duration | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14
1.0 | Project Initiation & Controls | Project Manager | Phase | 2026-07-27 | 2026-07-28 | 2 | bar: 2026-07-27 to 2026-08-14
1.1 | Confirm business objective and project sponsor | Project Manager | Task | 2026-07-27 | 2026-07-27 | 1 | bar: 2026-07-27
1.2 | Issue CTR – Cost, Time and Resource document | Project Manager | Task | 2026-07-27 | 2026-07-27 | 1 | bar: 2026-07-27
1.3 | Issue PMP and project organization | Project Manager | Task | 2026-07-27 | 2026-07-27 | 1 | bar: 2026-07-27
1.4 | Issue NCD and rollback plan | Linux Lead | Task | 2026-07-28 | 2026-07-28 | 1 | bar: 2026-07-28
1.5 | Issue ITQ register and close critical queries | Project Manager | Task | 2026-07-28 | 2026-07-28 | 1 | bar: 2026-07-28
2.0 | Design & Readiness | Linux Lead | Phase | 2026-07-29 | 2026-07-31 | 3 | bar: 2026-07-27 to 2026-08-14
2.1 | Complete VM inventory and student assignments | Lab Administrator | Task | 2026-07-29 | 2026-07-29 | 1 | bar: 2026-07-29
2.2 | Confirm root access, repositories and packages | Student Team | Task | 2026-07-29 | 2026-07-29 | 1 | bar: 2026-07-29
2.3 | Create Xen Orchestra pre-change snapshots | Lab Administrator | Task | 2026-07-30 | 2026-07-30 | 1 | bar: 2026-07-30
2.4 | Review FDS, acceptance criteria and evidence rules | Instructor | Task | 2026-07-30 | 2026-07-30 | 1 | bar: 2026-07-30
2.5 | Go / No-Go review | Project Manager | Milestone | 2026-07-31 | 2026-07-31 | 0 | bar: 2026-07-31
3.0 | Technical Build | Student Team | Phase | 2026-08-03 | 2026-08-06 | 4 | bar: 2026-07-27 to 2026-08-14
3.1 | Create report-generator and job-control exercises | Student Team | Task | 2026-08-03 | 2026-08-03 | 1 | bar: 2026-08-03
3.2 | Complete signal-management tests | Student Team | Task | 2026-08-04 | 2026-08-04 | 1 | bar: 2026-08-04
3.3 | Create CPU worker and priority tests | Student Team | Task | 2026-08-04 | 2026-08-04 | 1 | bar: 2026-08-04
3.4 | Complete nohup and /proc exercises | Student Team | Task | 2026-08-05 | 2026-08-05 | 1 | bar: 2026-08-05
3.5 | Create parent-child and zombie demonstrations | Student Team | Task | 2026-08-05 | 2026-08-05 | 1 | bar: 2026-08-05
3.6 | Create reportsvc and systemd service | Student Team | Task | 2026-08-06 | 2026-08-06 | 1 | bar: 2026-08-06
4.0 | Testing & Incident Simulation | Linux Lead | Phase | 2026-08-07 | 2026-08-11 | 3 | bar: 2026-07-27 to 2026-08-14
4.1 | Execute automated validation tests | Student Team | Task | 2026-08-07 | 2026-08-07 | 1 | bar: 2026-08-07
4.2 | Run high-CPU bank incident scenario | Instructor / Students | Task | 2026-08-10 | 2026-08-10 | 1 | bar: 2026-08-10
4.3 | Restore service and confirm business acceptance | Student Team | Task | 2026-08-11 | 2026-08-11 | 1 | bar: 2026-08-11
4.4 | Technical acceptance review | Linux Lead | Milestone | 2026-08-11 | 2026-08-11 | 0 | bar: 2026-08-11
5.0 | Handover & Closure | Project Manager | Phase | 2026-08-12 | 2026-08-14 | 3 | bar: 2026-07-27 to 2026-08-14
5.1 | Complete incident report and lessons learned | Student Team | Task | 2026-08-12 | 2026-08-12 | 1 | bar: 2026-08-12
5.2 | Update final documents and evidence register | Document Controller | Task | 2026-08-13 | 2026-08-13 | 1 | bar: 2026-08-13
5.3 | Knowledge-transfer presentation | Student Team | Task | 2026-08-14 | 2026-08-14 | 1 | bar: 2026-08-14
5.4 | Business acceptance and project closure | Business Owner | Milestone | 2026-08-14 | 2026-08-14 | 0 | bar: 2026-08-14