## NCD Overview
NCD – Implementation, Validation and Rollback Runbook
Business-controlled change document for the NIT Bank Linux Process Operations Lab.
1. Change Metadata
Field | Value | Field | Value | Field | Value
NCD / Change ID | NIT-BANK-LPX-001 | Change Status | Planning | Risk Rating | Medium
Change Title | Deploy the Linux process-management training project | Environment | Classroom / Xen Orchestra | Change Type | Normal Training Change
Planned Date | 2026-07-27 | Planned Start | 09:00 | Planned End | 16:00
Implementer | Student Team | Change Manager | Instructor / Project Manager | Technical Owner | Linux Lead Instructor
Business Owner | NIT Bank Operations Training | Primary Platform | One Rocky Linux VM per student | Student VM Count | TBD
Source Document | Linux Process Management FDS | Platform | Rocky Linux 9 / Xen Orchestra | Change Window TZ | America/Chicago
2. Execution Dashboard
Metric | Value |  | Phase | Step Count | Completed | Control | Status | Comments / Evidence
Total Runbook Steps | 62 |  | A. Pre-Implementation | 11 | 0 | Change approved | Pending
Completed | 0 |  | B. Implementation | 30 | 0 | Snapshot completed | Pending
In Progress | 0 |  | C. Post-Implementation Validation | 12 | 0 | Root access and packages ready | Pending
Failed | 0 |  | D. Rollback | 9 | 0 | Rollback owner available | Pending
Rolled Back | 0 |  | Go / No-Go Indicator | GO | No failed steps recorded | Go / No-Go authorization | Pending
Overall Completion | 0%
3. Scope, Business Impact and Backout Criteria
Item | Details
In Scope | Create and test the report-generator, CPU worker, parent-child and zombie demonstrations; use ps/top/pgrep/pstree, signals, nice/renice, nohup, /proc and systemd; complete incident recovery and evidence.
Out of Scope | Production banking applications, real customer data, internet-facing services, high availability, enterprise monitoring integration and changes to shared infrastructure.
Expected Business Impact | Students learn how a controlled technology change is planned, approved, executed, validated and closed. Each student works only inside an assigned training VM.
Rollback Triggers | Assigned VM becomes unstable; CPU worker cannot be controlled; systemd service repeatedly fails; required validation cannot be completed; unauthorized scope change; loss of SSH without console recovery.
Preferred Backout Method | Stop lab processes, disable/remove the report-generator service, restore configuration files, and revert the Xen Orchestra pre-change snapshot when required.
4. Student Usage Instructions
1 | Work from the approved business documents before running technical commands.
2 | Confirm that `whoami` returns root and that the VM is the student's assigned Xen Orchestra VM.
3 | Record screenshots, command output, ticket references or log excerpts as evidence.
4 | Update every runbook step to Complete, Failed, Skipped or Rolled Back.
5 | A failed mandatory gate is a stop point and must be escalated to the instructor/project manager.
6 | Do not use real bank information, customer data or production credentials in this training project.

## Process Flow
NIT Bank Linux Process Project – Business and Technical Flow
From business request to controlled implementation, validation, acceptance and closure.
1. Business Need Train junior Linux operations staff |  |  | 2. CTR & PMP Define scope, cost, time and resources |  |  | 3. NCD & ITQ Approve change and resolve open inputs |  |  | 4. Build Create scripts and process scenarios
|  | → |  |  | → |  |  | →
↑ | [9 empty] | ↓
8. Handover & Closure Lessons learned and business value |  |  | 7. Validation Evidence, acceptance criteria and sign-off |  |  | 6. Incident Simulation High CPU and failed service |  |  | 5. Test Signals, priorities, /proc, zombie, systemd
|  | ← |  |  | ← |  |  | ←
Business Controls Across Every Stage
Scope Control | Change Approval | Risk Management | Resource Planning | Document Control | Quality / Testing | Evidence | Acceptance | Cost Awareness | Schedule Tracking | Rollback Readiness | Lessons Learned
CTR | NCD | Risk Register | PMP | MDL / Revision | Validation Plan | Screenshots / Logs | Sign-off | Cost Model | Master Schedule | Snapshot / Cleanup | Closure Report

## Inventory
VM, Process and Configuration Inventory
Complete before implementation and update after final validation.
Record ID | Business Role | Hostname | Student / Owner | IP Address | OS / Version | vCPU | RAM (GB) | Disk (GB) | Root Access | Snapshot ID | Project Directory | Service Name | Service Account | Main PID | Status | Evidence Ref | Notes
PLT-01 | Xen Orchestra Platform | nit-xcp01 | Lab Administrator | 192.168.1.x | XCP-ng / XO |  |  |  | Admin | TBD | N/A | N/A | N/A |  | Ready |  | Shared hypervisor; students must not modify other VMs.
VM-01 | Student Bank Process Lab VM | lab-process-01 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-02 | Student Bank Process Lab VM | lab-process-02 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-03 | Student Bank Process Lab VM | lab-process-03 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-04 | Student Bank Process Lab VM | lab-process-04 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-05 | Student Bank Process Lab VM | lab-process-05 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-06 | Student Bank Process Lab VM | lab-process-06 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-07 | Student Bank Process Lab VM | lab-process-07 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-08 | Student Bank Process Lab VM | lab-process-08 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-09 | Student Bank Process Lab VM | lab-process-09 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-10 | Student Bank Process Lab VM | lab-process-10 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-11 | Student Bank Process Lab VM | lab-process-11 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-12 | Student Bank Process Lab VM | lab-process-12 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-13 | Student Bank Process Lab VM | lab-process-13 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.
VM-14 | Student Bank Process Lab VM | lab-process-14 |  |  | Rocky Linux 9 | 1 | 1 | 20 | Yes |  | /opt/process-lab | report-generator.service | reportsvc |  | Planned |  | One assigned VM per student; replace values before execution.

## Dependencies
Access, Package, Process and Service Dependencies
Business and technical prerequisites that must be confirmed before implementation.
ID | Category | Dependency / Input | Provided By | Needed For | Pre-Check / Command | Expected Result | Business Risk if Missing | Resolution Owner | Status | Approval / Notes
D01 | Access | Assigned Rocky Linux 9 VM with root account | Lab Administrator | All technical activities | whoami; id | root / uid=0 | Student cannot complete the lab | Xen Orchestra Admin | Pending
D02 | Recovery | Pre-change Xen Orchestra snapshot | Student / Lab Admin | Rollback | Record snapshot name and time | Snapshot available | Longer recovery and possible rebuild | Lab Administrator | Pending
D03 | Package | procps-ng | Rocky repository | ps, top, pgrep | rpm -q procps-ng | Installed | Core monitoring commands missing | Student | Pending
D04 | Package | psmisc | Rocky repository | pstree and process tools | rpm -q psmisc | Installed | Parent-child view unavailable | Student | Pending
D05 | Package | gcc | Rocky repository | Zombie C program | rpm -q gcc | Installed | Zombie exercise cannot be compiled | Student | Pending
D06 | Service | systemd operational | Rocky Linux | Service management | systemctl is-system-running | running or degraded with explanation | Service lab unavailable | Student | Pending
D07 | Filesystem | /opt/process-lab writable | Student root account | Project files | test -d /opt/process-lab | Directory exists | Scripts cannot be stored consistently | Student | Pending
D08 | Filesystem | /proc mounted | Linux kernel | Process inspection | mount ¦ grep ' on /proc ' | proc filesystem mounted | Process internals unavailable | Student | Pending
D09 | Network | SSH TCP 22 or Xen Orchestra console | Lab Administrator | Student access | ss -lntp ¦ grep :22 | Approved access works | Student locked out | Xen Orchestra Admin | Pending
D10 | Business | Approved student roster and VM assignment | Instructor | Accountability and evidence | Review roster | Every student mapped to one VM | Evidence cannot be attributed | Instructor | Pending
D11 | Business | Evidence storage location | Instructor | Acceptance and grading | Confirm LMS/Drive folder | Location approved | Evidence lost or inconsistent | Document Controller | Pending
D12 | Governance | No real bank/customer data used | Instructor / Students | Privacy and safety | Review scenario data | Synthetic data only | Privacy/compliance issue | Project Manager | Pending

## Implementation Plan
Master NCD Execution Plan – Execute in Sequence
All commands assume students are logged in directly as root on their assigned Rocky Linux VM.
Change ID | NIT-BANK-LPX-001 | Planned Window | 2026-07-27 to 2026-08-14 | Implementer | Student Team | Change Manager | Instructor | Technical Owner | Linux Lead | Status | Draft
Seq | Phase | Step ID | Gate | Target Host / Role | Procedure / Action | Command / Navigation | Expected Result | Comments / Dependencies | Status | Owner | Planned Duration (min) | Start Time | End Time | Actual Result / Evidence | Rollback Ref | Actual Duration (min)
1 | A. Pre-Implementation | A01 | Mandatory | Change record | Confirm project approval and authorized training scope. | Review CTR, PMP, NCD, Master Schedule and instructor approval. | Approved scope and project window confirmed. | Do not begin technical work without approval. | Not Started | Project Manager | 10
2 | A. Pre-Implementation | A02 | Mandatory | Student / VM | Confirm the student is on the assigned VM. | hostnamectl; ip -4 addr; compare with Inventory sheet | Hostname/IP match the assigned inventory record. | Never work on another student's VM. | Not Started | Student | 10
3 | A. Pre-Implementation | A03 | Mandatory | Student account | Verify root access. | whoami; id | whoami=root and uid=0(root). | All project commands assume direct root login. | Not Started | Student | 5
4 | A. Pre-Implementation | A04 | Mandatory | VM | Record baseline resources. | lscpu; free -h; lsblk; df -h; uptime | CPU, RAM, disk and load baseline captured. | Attach output as evidence. | Not Started | Student | 10
5 | A. Pre-Implementation | A05 | Mandatory | VM | Check required repositories. | dnf repolist | Rocky repositories available. | Escalate repository failures before package installation. | Not Started | Student | 5
6 | A. Pre-Implementation | A06 | Mandatory | VM | Install required packages. | dnf install -y procps-ng psmisc gcc tree | All required packages install successfully. | Use only approved Rocky repositories. | Not Started | Student | 15 |  |  |  | D04
7 | A. Pre-Implementation | A07 | Mandatory | VM | Verify required packages. | rpm -q procps-ng psmisc gcc tree | Installed package versions displayed. | Record versions in evidence. | Not Started | Student | 5
8 | A. Pre-Implementation | A08 | Mandatory | Xen Orchestra | Create a pre-change snapshot. | XO → VM → Snapshots → New snapshot; name <CHANGE_ID>-pre | Snapshot ID/name recorded in Inventory. | Snapshot is the preferred full-VM rollback. | Not Started | Student / Lab Admin | 10 |  |  |  | D01
9 | A. Pre-Implementation | A09 | Mandatory | VM | Confirm no conflicting lab processes are running. | pgrep -af 'report-generator¦cpu-worker¦parent-child¦zombie' | No old project processes remain. | Stop old processes before continuing. | Not Started | Student | 5 |  |  |  | D02
10 | A. Pre-Implementation | A10 | Mandatory | Business controls | Confirm evidence location and naming convention. | Create folder: StudentName/Process-Project/Evidence | Evidence folder is available. | Use synthetic bank scenario only. | Not Started | Student | 5
11 | A. Pre-Implementation | A11 | Decision | Change review | Conduct Go / No-Go review. | Review approvals, root access, packages, snapshot and VM assignment. | GO recorded before B01. | Any missing mandatory prerequisite results in NO-GO. | Not Started | Project Manager | 10
12 | B. Implementation | B01 | Mandatory | VM | Create project directory. | mkdir -p /opt/process-lab; chown root:root /opt/process-lab; cd /opt/process-lab | Directory exists and is owned by root. | Standard project location supports repeatability. | Not Started | Student | 5 |  |  |  | D03
13 | B. Implementation | B02 | Mandatory | Report generator | Create the report-generator script. | Create /opt/process-lab/report-generator.sh from the approved lab guide. | Executable script exists. | Use the controlled script supplied in the FDS/runbook. | Not Started | Student | 15 |  |  |  | D03
14 | B. Implementation | B03 | Mandatory | Report generator | Validate Bash syntax and permissions. | bash -n /opt/process-lab/report-generator.sh; chmod 755 /opt/process-lab/report-generator.sh | No syntax errors; executable permission present. | Do not continue with syntax errors. | Not Started | Student | 5
15 | B. Implementation | B04 | Mandatory | Shell | Run the report generator in foreground. | /opt/process-lab/report-generator.sh | Terminal remains occupied; log entries are created. | Use a second terminal for observation. | Not Started | Student | 10 |  |  |  | D02
16 | B. Implementation | B05 | Mandatory | Process monitoring | Identify the foreground process. | pgrep -af report-generator; ps -o user,pid,ppid,stat,etime,cmd -p <PID> | PID, PPID, owner and state identified. | Record PID and evidence. | Not Started | Student | 10
17 | B. Implementation | B06 | Mandatory | Shell | Stop the foreground process with Ctrl+C. | Ctrl+C; pgrep -af report-generator | Process stops and is no longer listed. | Ctrl+C normally sends SIGINT. | Not Started | Student | 5
18 | B. Implementation | B07 | Mandatory | Shell jobs | Start report generator in background. | /opt/process-lab/report-generator.sh &; jobs -l | Job number and PID displayed. | Explain job number versus PID. | Not Started | Student | 10 |  |  |  | D02
19 | B. Implementation | B08 | Mandatory | Shell jobs | Move job foreground, suspend and resume. | fg %1; Ctrl+Z; jobs -l; bg %1 | Job changes between foreground, stopped and background states. | Stopped state normally includes T. | Not Started | Student | 15
20 | B. Implementation | B09 | Mandatory | Signals | Send SIGSTOP and confirm state. | kill -STOP <PID>; ps -o pid,ppid,stat,cmd -p <PID> | State includes T and log output pauses. | Record before/after log timestamps. | Not Started | Student | 10
21 | B. Implementation | B10 | Mandatory | Signals | Resume with SIGCONT. | kill -CONT <PID>; sleep 12; tail -n 5 /tmp/report-generator.log | Process resumes and new log entries appear. | SIGCONT resumes a stopped process. | Not Started | Student | 10
22 | B. Implementation | B11 | Mandatory | Signals | Terminate gracefully with SIGTERM. | kill -15 <PID>; ps -p <PID> | Process terminates. | SIGTERM should normally be attempted first. | Not Started | Student | 10
23 | B. Implementation | B12 | Mandatory | Signals | Demonstrate forced termination with SIGKILL. | Start script; kill -9 <PID>; ps -p <PID> | Process is immediately removed. | Use only for demonstration or unresponsive processes. | Not Started | Student | 10
24 | B. Implementation | B13 | Mandatory | CPU worker | Create and validate cpu-worker.sh. | Create script; bash -n /opt/process-lab/cpu-worker.sh; chmod 755 ... | CPU worker is executable and syntax-valid. | Run only one worker. | Not Started | Student | 15 |  |  |  | D02
25 | B. Implementation | B14 | Mandatory | CPU worker | Start the CPU worker and save its PID. | /opt/process-lab/cpu-worker.sh &; CPU_PID=$!; echo $CPU_PID | CPU worker PID recorded. | This deliberately consumes one CPU core. | Not Started | Student | 5 |  |  |  | D02
26 | B. Implementation | B15 | Mandatory | Monitoring | Identify the high-CPU process. | top; ps -eo pid,ppid,user,stat,%cpu,%mem,ni,cmd --sort=-%cpu ¦ head | CPU worker appears near top of list. | Capture evidence before remediation. | Not Started | Student | 10
27 | B. Implementation | B16 | Mandatory | Priority | Change running priority. | renice 10 -p <CPU_PID>; ps -o pid,ni,pri,%cpu,cmd -p <CPU_PID> | Nice value becomes 10. | Higher nice value means lower scheduling priority. | Not Started | Student | 10
28 | B. Implementation | B17 | Mandatory | Priority | Start a process with nice value 15. | nice -n 15 /opt/process-lab/cpu-worker.sh & | New process shows NI=15. | Stop both workers after comparison. | Not Started | Student | 10
29 | B. Implementation | B18 | Mandatory | CPU worker | Stop all CPU workers. | pkill -TERM -f /opt/process-lab/cpu-worker.sh; pgrep -af cpu-worker | No CPU worker remains. | Use SIGKILL only if required. | Not Started | Student | 5 |  |  |  | D02
30 | B. Implementation | B19 | Mandatory | nohup | Start report generator with nohup. | nohup /opt/process-lab/report-generator.sh > /tmp/report-output.log 2>&1 & | Process starts and PID is recorded. | Save PID in /tmp/nohup-report.pid. | Not Started | Student | 10 |  |  |  | D02
31 | B. Implementation | B20 | Mandatory | SSH session | Test that nohup survives logout. | exit; reconnect; ps -p $(cat /tmp/nohup-report.pid) | Process still running after reconnect. | Use Xen Orchestra console if needed. | Not Started | Student | 15
32 | B. Implementation | B21 | Mandatory | /proc | Inspect process status, command line, file descriptors and limits. | cat /proc/<PID>/status; tr '\0' ' ' < /proc/<PID>/cmdline; ls -l /proc/<PID>/fd; cat /proc/<PID>/limits | Required process details recorded. | Do not expose sensitive environment variables. | Not Started | Student | 20
33 | B. Implementation | B22 | Mandatory | Parent-child | Create and run parent-child.sh. | Create script; chmod 755; /opt/process-lab/parent-child.sh & | Parent and two sleep children run. | Record parent PID. | Not Started | Student | 15 |  |  |  | D02
34 | B. Implementation | B23 | Mandatory | Process tree | Display the hierarchy. | pstree -p <PARENT_PID>; pgrep -P <PARENT_PID> -a | Parent-child relationship is visible. | Include screenshot/output. | Not Started | Student | 10
35 | B. Implementation | B24 | Mandatory | Zombie program | Create and compile zombie.c. | gcc /opt/process-lab/zombie.c -o /opt/process-lab/zombie | Executable is produced. | gcc dependency must be installed. | Not Started | Student | 15 |  |  |  | D03
36 | B. Implementation | B25 | Mandatory | Zombie process | Run and identify zombie state. | /opt/process-lab/zombie &; ps -eo pid,ppid,stat,cmd ¦ awk '$3 ~ /^Z/' | Child process displays Z / <defunct>. | Zombie is already terminated; parent has not reaped it. | Not Started | Student | 15
37 | B. Implementation | B26 | Mandatory | Zombie process | Remove the lab zombie by terminating parent. | kill -15 <ZOMBIE_PARENT>; sleep 2; repeat zombie search | Lab zombie disappears. | Do not kill unrelated system processes. | Not Started | Student | 5
38 | B. Implementation | B27 | Mandatory | Service account | Create reportsvc system account. | useradd --system --home-dir /opt/process-lab --shell /sbin/nologin reportsvc ¦¦ id reportsvc | Service account exists. | Least-privilege service ownership is a business control. | Not Started | Student | 10 |  |  |  | D03
39 | B. Implementation | B28 | Mandatory | systemd | Create signal-aware report-generator script and service unit. | Create /etc/systemd/system/report-generator.service according to FDS. | Unit file and script exist with correct permissions. | Service runs as reportsvc, not root. | Not Started | Student | 20 |  |  |  | D03
40 | B. Implementation | B29 | Mandatory | systemd | Validate and start the service. | systemd-analyze verify /etc/systemd/system/report-generator.service; systemctl daemon-reload; systemctl enable --now report-generator | Service becomes active and enabled. | Stop on unit validation errors. | Not Started | Student | 15 |  |  |  | D03
41 | B. Implementation | B30 | Mandatory | systemd | Test service restart-on-failure. | SERVICE_PID=$(systemctl show report-generator --property=MainPID --value); kill -9 $SERVICE_PID; sleep 7; systemctl status report-generator --no-pager | systemd restarts service with a new PID. | Demonstrates operational resilience. | Not Started | Student | 15
42 | C. Post-Implementation Validation | C01 | Mandatory | Project files | Validate required files and executables. | ls -l /opt/process-lab; bash -n /opt/process-lab/*.sh | Required files exist; scripts pass syntax checks. | Attach listing. | Not Started | Student | 10
43 | C. Post-Implementation Validation | C02 | Mandatory | Service | Confirm service active and enabled. | systemctl is-active report-generator; systemctl is-enabled report-generator | Outputs active and enabled. | Failure blocks acceptance. | Not Started | Student | 5
44 | C. Post-Implementation Validation | C03 | Mandatory | Service process | Confirm service account and MainPID. | systemctl show report-generator --property=MainPID; ps -o user,pid,ppid,stat,cmd -p <PID> | Valid PID; owner is reportsvc. | Least privilege verified. | Not Started | Student | 10
45 | C. Post-Implementation Validation | C04 | Mandatory | Logs | Confirm operational log growth. | tail -n 5 /tmp/report-generator.log; sleep 12; tail -n 5 /tmp/report-generator.log | New timestamped entries appear. | Demonstrates service operation. | Not Started | Student | 15
46 | C. Post-Implementation Validation | C05 | Mandatory | Incident simulation | Start one CPU worker as the fault condition. | runuser -u reportsvc -- nohup /opt/process-lab/cpu-worker.sh > /tmp/cpu-worker.out 2>&1 & | High-CPU process starts under reportsvc. | Controlled classroom fault only. | Not Started | Instructor / Student | 5 |  |  |  | D02
47 | C. Post-Implementation Validation | C06 | Mandatory | Incident response | Identify the high-CPU process and system load. | uptime; top; ps -eo pid,ppid,user,stat,%cpu,%mem,ni,etime,cmd --sort=-%cpu ¦ head | Fault process and impact identified. | Evidence must be captured before correction. | Not Started | Student | 10
48 | C. Post-Implementation Validation | C07 | Mandatory | Incident response | Lower priority and terminate safely. | renice 15 -p <PID>; kill -15 <PID>; sleep 2; ps -p <PID> | Nice value changes and process terminates. | Escalate to SIGKILL only if required. | Not Started | Student | 10
49 | C. Post-Implementation Validation | C08 | Mandatory | Service recovery | Restart and validate report service. | systemctl restart report-generator; systemctl status report-generator --no-pager | Service is restored and stable. | Record recovery time. | Not Started | Student | 10
50 | C. Post-Implementation Validation | C09 | Mandatory | Automated validation | Run the project validation script. | /opt/process-lab/validate-project.sh | PROJECT VALIDATION SUCCESSFUL. | All failed checks must be corrected. | Not Started | Student | 10
51 | C. Post-Implementation Validation | C10 | Mandatory | Evidence | Complete Validation Evidence sheet. | Record actual result, pass/fail, evidence reference, tester and timestamp. | Every acceptance test has traceable evidence. | Missing evidence means incomplete delivery. | Not Started | Student | 20
52 | C. Post-Implementation Validation | C11 | Mandatory | Business acceptance | Complete incident report and lessons learned. | Use approved incident-report template. | Root cause, actions, validation and prevention documented. | Technical work must be translated into business language. | Not Started | Student | 25
53 | C. Post-Implementation Validation | C12 | Mandatory | Change closure | Obtain instructor acceptance and close the change. | Review deliverables, evidence, risks and open actions. | Project accepted or punch-list issued. | Close only after mandatory criteria pass. | Not Started | Project Manager | 15
54 | D. Rollback | D01 | Decision | Change review | Declare rollback and obtain authorization. | Record failure, impact, selected backout and authorization time. | Rollback decision documented. | Do not perform destructive rollback without approval. | Not Started | Project Manager | 5
55 | D. Rollback | D02 | Mandatory | Processes | Stop all lab processes. | pkill -TERM -f '/opt/process-lab/report-generator.sh¦/opt/process-lab/cpu-worker.sh¦/opt/process-lab/parent-child.sh¦/opt/process-lab/zombie' | All lab processes stopped. | Verify PIDs before using SIGKILL. | Not Started | Student | 10
56 | D. Rollback | D03 | Mandatory | systemd | Disable and remove the service. | systemctl disable --now report-generator; rm -f /etc/systemd/system/report-generator.service; systemctl daemon-reload; systemctl reset-failed | Service removed and no longer enabled. | Preserve evidence before removal. | Not Started | Student | 10
57 | D. Rollback | D04 | Conditional | Service account | Remove reportsvc if created only for this lab. | userdel reportsvc | Lab service account removed. | Do not remove if used by another approved service. | Not Started | Student | 5
58 | D. Rollback | D05 | Conditional | Project files | Archive or remove lab directory. | tar -czf /root/<CHANGE_ID>-evidence.tgz /opt/process-lab; rm -rf /opt/process-lab | Evidence archived; project files removed. | Confirm archive before deletion. | Not Started | Student | 10
59 | D. Rollback | D06 | Conditional | Temporary files | Remove temporary project logs. | rm -f /tmp/report-generator.log /tmp/report-output.log /tmp/nohup-report.pid /tmp/cpu-worker.out | Temporary files removed. | Do not use broad /tmp deletion commands. | Not Started | Student | 5
60 | D. Rollback | D07 | Conditional | VM | Revert the Xen Orchestra snapshot. | XO → VM → Snapshots → Revert approved pre-change snapshot | VM returns to pre-change state. | Use when manual rollback is insufficient. | Not Started | Lab Administrator | 15
61 | D. Rollback | D08 | Mandatory | Validation | Confirm rollback state. | pgrep -af 'report-generator¦cpu-worker¦parent-child¦zombie'; systemctl status report-generator | No lab processes/service remain unless intentionally retained. | Record final evidence. | Not Started | Student | 10
62 | D. Rollback | D09 | Mandatory | Change record | Document rollback result and close/escalate. | Update NCD, risk, incident and lessons learned. | Rollback outcome and follow-up owner recorded. | Unresolved issues remain open with owner/date. | Not Started | Project Manager | 10

## Validation Evidence
Post-Implementation Validation Evidence Log
Formal acceptance evidence for technical and business validation.
Test ID | Runbook Step | Category | Target Host / Service | Validation Test | Command / Navigation | Expected Result | Actual Result | Pass / Fail | Evidence Reference | Tester | Timestamp
VAL-01 | A03 | Access | Student VM | Root access verified | whoami; id | root / uid=0 |  | Not Run
VAL-02 | A08 | Recovery | Xen Orchestra | Snapshot recorded | Review Inventory | Snapshot ID/name present |  | Not Run
VAL-03 | B03 | Scripts | Student VM | Bash syntax valid | bash -n /opt/process-lab/*.sh | No syntax errors |  | Not Run
VAL-04 | B05 | Process ID | Report generator | PID and PPID identified | ps / pgrep | Correct process details |  | Not Run
VAL-05 | B08 | Job control | Shell | fg/bg/jobs behavior | jobs -l; fg; bg | Expected state transitions |  | Not Run
VAL-06 | B09-B12 | Signals | Report generator | STOP/CONT/TERM/KILL demonstrated | kill commands and ps | Correct process behavior |  | Not Run
VAL-07 | B15 | CPU | CPU worker | High CPU detected | top / ps sorted by CPU | Worker identified |  | Not Run
VAL-08 | B16-B17 | Priority | CPU worker | nice/renice values confirmed | ps -o ni,pri | NI 10 and NI 15 observed |  | Not Run
VAL-09 | B20 | Persistence | nohup process | Survives logout | Reconnect and ps | Same PID still running |  | Not Run
VAL-10 | B21 | /proc | Report process | Process details inspected | /proc/<PID> | Status, limits and FDs recorded |  | Not Run
VAL-11 | B23 | Hierarchy | Parent-child script | Process tree visible | pstree -p | Parent and two children shown |  | Not Run
VAL-12 | B25 | Zombie | Zombie program | Zombie state identified | ps STAT | Z / defunct observed |  | Not Run
VAL-13 | B29 | systemd | report-generator.service | Service active and enabled | systemctl | active and enabled |  | Not Run
VAL-14 | B30 | Resilience | systemd | Restart on failure | kill -9 MainPID | New PID after restart |  | Not Run
VAL-15 | C03 | Least privilege | Service process | Runs as reportsvc | ps -o user | Owner reportsvc |  | Not Run
VAL-16 | C04 | Logging | Report service | Log growth confirmed | tail / sleep / tail | New timestamps |  | Not Run
VAL-17 | C06-C08 | Incident | Student VM | High CPU incident resolved | uptime/top/renice/kill/systemctl | Worker stopped; service healthy |  | Not Run
VAL-18 | C09 | Automation | Project validator | Validation script passes | validate-project.sh | PROJECT VALIDATION SUCCESSFUL |  | Not Run
VAL-19 | C11 | Business | Incident report | Report complete | Document review | Root cause/actions/validation included |  | Not Run
VAL-20 | C12 | Acceptance | Change record | Instructor sign-off | Approval review | Accepted / punch list |  | Not Run

## Approvals & Contacts
Approvals, Contacts and Execution Sign-Off
Business ownership, technical accountability and formal project acceptance.
Change Team and Escalation Contacts
Role | Name | Team | Phone / Bridge | Email / Chat | Available From | Available Until | Notes
Project Sponsor / Business Owner |  | NIT Bank Operations Training |  |  |  |  | Approves business objective and acceptance.
Project Manager / Instructor |  | Training Delivery |  |  |  |  | Owns scope, schedule, cost and change approval.
Linux Technical Lead |  | Linux Operations |  |  |  |  | Owns technical standard and troubleshooting escalation.
Xen Orchestra Administrator |  | Lab Infrastructure |  |  |  |  | Owns VM assignment, console and snapshots.
Document Controller |  | Project Controls |  |  |  |  | Owns revisions, evidence and final document pack.
Student Team Lead |  | Student Team |  |  |  |  | Coordinates execution and evidence.
Approval and Sign-Off Log
Stage | Decision | Approver | Role | Date / Time | Evidence / Ticket Ref | Comments | Signature / Initials
Project Charter / CTR Approval | Pending |  | Business Owner
NCD / Change Approval | Pending |  | Project Manager
Go / No-Go | Pending |  | Project Manager
Post-Implementation Technical Validation | Pending |  | Linux Technical Lead
Student Deliverable Acceptance | Pending |  | Instructor
Rollback Authorization (if used) | Not Applicable |  | Project Manager
Project Closure | Pending |  | Business Owner / PM