## PMP Overview
PROJECT MANAGEMENT PLAN (PMP)
NIT Bank Linux Process Operations Lab – Business governance, organization, controls and delivery model.
1. Project Purpose
Business Need | NIT Bank requires junior Linux operations staff to understand how process incidents are controlled, diagnosed, recovered and documented.
Project Objective | Deliver a repeatable classroom project that combines Linux process management with scope, cost, schedule, risk, change control, evidence, acceptance and handover.
Success Definition | Students complete the technical lab, pass validation, resolve the simulated incident, submit business documents and obtain instructor acceptance.
2. Governance and Project Controls
Control Area | Primary Document | Owner | Review Frequency | Approval / Output | Business Purpose | Status | Comments
Scope | CTR / FDS | Project Manager | At start and on change | Approved scope | Prevents uncontrolled technical additions | Planned
Schedule | Master Schedule | Project Manager | Weekly | Updated baseline / forecast | Makes delivery dates visible | Planned
Cost & Resources | CTR / Cost Model | Project Manager | Weekly | Forecast at completion | Shows business effort and affordability | Planned
Change | NCD | Change Manager / Instructor | Before implementation | Go / No-Go | Protects the lab and creates accountability | Planned
Interfaces / Queries | ITQ Register | Business Analyst | Twice weekly | Closed decisions | Prevents assumptions from becoming defects | Planned
Risk | Risk Register | Project Manager | Weekly | Mitigation actions | Reduces technical and business surprises | Planned
Quality | FDS / Validation Evidence | Linux Lead | At design and testing | Technical acceptance | Defines measurable success | Planned
Documents | Master Document List | Document Controller | Continuous | Controlled revisions | Ensures traceability and professional handover | Planned
Acceptance | Sign-off Register | Business Owner / Instructor | At project end | Project closure | Confirms value was delivered | Planned
3. Communication Plan
Meeting / Report | Audience | Frequency | Owner | Inputs | Outputs | Channel | Record
Project Kickoff | Sponsor, PM, Technical Lead, Lab Admin, Students | Once | Project Manager | CTR, PMP, Schedule | Approved roles and objectives | Class / Video Call | Minutes
Daily Lab Brief | Instructor and Students | Daily | Instructor | Runbook, open issues | Daily priorities and safety reminders | Classroom | Attendance / notes
Weekly Status Review | Sponsor, PM, Technical Lead | Weekly | Project Manager | Schedule, cost, risks, ITQs | RAG status and decisions | Meeting | Status report
Go / No-Go Review | PM, Linux Lead, Lab Admin, Students | Before build | Project Manager | NCD prerequisites | GO / NO-GO decision | Change review | Approval log
Incident Review | Instructor and Students | During simulation | Linux Lead | Monitoring evidence | Root cause and recovery decision | Classroom | Incident log
Acceptance Review | Sponsor, PM, Instructor, Students | Project end | Project Manager | Deliverables and evidence | Acceptance / punch list | Presentation | Sign-off

## Deliverables & Cost
Deliverables, Planned Effort and Cost Model
A training estimate showing how business documents and technical work consume resources.
Deliverable / Work Package | Project Manager Hrs | Linux Lead Hrs | Lab Admin Hrs | Document Control Hrs | Student Hrs | Total Hrs | Estimated Cost (USD)
Project Management Plan (PMP) | 6 | 1 | 0 | 4 | 0 | 11 | 515
CTR – Cost, Time and Resource | 4 | 1 | 0 | 3 | 0 | 8 | 375
Master Schedule and Tracker | 4 | 1 | 0 | 3 | 0 | 8 | 375
NCD / Change Runbook | 3 | 6 | 2 | 2 | 0 | 13 | 650
ITQ / Interface Register | 3 | 2 | 1 | 4 | 0 | 10 | 465
Functional Design Specification | 2 | 8 | 1 | 4 | 0 | 15 | 745
VM Readiness and Snapshots | 1 | 2 | 8 | 1 | 7 | 19 | 560
Process Scripts and Exercises | 1 | 8 | 1 | 1 | 35 | 46 | 575
systemd Service Implementation | 1 | 5 | 1 | 1 | 14 | 22 | 410
Testing and Validation Evidence | 2 | 6 | 2 | 4 | 21 | 35 | 680
Incident Simulation and Recovery | 2 | 5 | 1 | 2 | 14 | 24 | 500
Training Presentation and Handover | 4 | 2 | 1 | 3 | 7 | 17 | 475
Project Closure and Lessons Learned | 4 | 1 | 0 | 2 | 7 | 14 | 335
TOTAL | [5 empty] | 242 | 6660
Role Rate Assumptions
Role | Hourly Rate | Planned Hours | Planned Cost
Project Manager / Instructor | 50 | 37 | 1850
Linux Technical Lead | 55 | 48 | 2640
Xen Orchestra / Lab Administrator | 45 | 18 | 810
Business Analyst / Document Controller | 40 | 34 | 1360
Student Team | 0 | 105 | 0

## Personnel
Project Organization and Personnel Register
Role clarity connects technical work to business accountability.
No. | Role / Responsibility | Name | Accountability | Decision Authority | Backup / Delegate
1 | Project Sponsor / Business Owner |  | Owns business value, funding and final acceptance | Approve scope and closure
2 | Project Manager / Instructor |  | Owns scope, cost, schedule, risk and communications | Go / No-Go and corrective actions
3 | Linux Technical Lead |  | Owns FDS, technical standards, coaching and acceptance | Technical design and escalation
4 | Xen Orchestra / Lab Administrator |  | Owns VM assignment, console, snapshots and recovery | Infrastructure recovery
5 | Business Analyst / Document Controller |  | Owns CTR, ITQ, revisions, evidence and final pack | Document release
6 | Student Team Lead |  | Coordinates student execution, evidence and status | Team work allocation
7 | Students / Junior Linux Operators |  | Execute approved runbook and submit evidence | No scope change authority

## RACI
RACI Responsibility Matrix
R = Responsible, A = Accountable, C = Consulted, I = Informed.
Activity | Sponsor | Project Manager | Linux Lead | Lab Admin | Document Control | Student Lead | Students | Primary Output
Approve business objective | A | R | C | I | I | I | I | Approved charter
Approve CTR / cost baseline | A | R | C | I | C | I | I | Approved CTR
Approve NCD / Go-No-Go | I | A/R | C | C | I | I | I | GO decision
Allocate VMs and snapshots | I | A | C | R | I | C | I | Ready inventory
Produce FDS | I | A | R | C | C | I | I | Approved design
Execute process lab | I | A | C | C | I | R | R | Working lab
Run incident simulation | I | A | R | C | I | C | R | Incident evidence
Validate technical result | I | A | R | C | C | C | R | Validation log
Control documents and revisions | I | A | C | I | R | C | I | Final document pack
Accept and close project | A | R | C | I | C | I | I | Closure approval

## Risk Register
Project Risk Register
Probability × Impact = Risk Score. Owners must maintain mitigation and contingency actions.
Risk ID | Risk Description | Probability (1-5) | Impact (1-5) | Score | Rating | Mitigation | Contingency / Response | Owner | Status | Review Date
R1 | Student runs commands on the wrong VM | 2 | 5 | 10 | Medium | Use roster, hostname/IP check and one-VM-per-student rule. | Stop work, preserve evidence and involve lab administrator. | Student Lead | Open | 2026-07-27
R2 | CPU worker causes excessive shared-host load | 3 | 4 | 12 | Medium | Run one worker for a limited time and stop after evidence. | Terminate worker and suspend exercise. | Linux Lead | Open | 2026-07-27
R3 | No root access or credentials unavailable | 3 | 4 | 12 | Medium | Verify access before Go / No-Go. | Reissue credentials or reassign VM. | Lab Admin | Open | 2026-07-27
R4 | Package repositories unavailable | 2 | 3 | 6 | Low | Pre-check dnf repositories. | Use approved local cache or reschedule. | Lab Admin | Open | 2026-07-27
R5 | Student loses SSH access | 2 | 4 | 8 | Medium | Maintain Xen Orchestra console access. | Recover through console or snapshot. | Lab Admin | Open | 2026-07-27
R6 | Snapshot not created or storage is full | 2 | 5 | 10 | Medium | Mandatory snapshot gate and storage check. | Manual cleanup or VM rebuild. | Lab Admin | Open | 2026-07-27
R7 | Validation evidence is incomplete | 3 | 3 | 9 | Medium | Use evidence checklist and naming convention. | Issue punch list and extend submission. | Document Controller | Open | 2026-07-27
R8 | Students use real bank/customer data | 1 | 5 | 5 | Low | Synthetic scenario and explicit privacy rule. | Stop exercise, remove data and escalate. | Project Manager | Open | 2026-07-27
R9 | systemd service runs as root instead of reportsvc | 2 | 4 | 8 | Medium | Acceptance test checks process owner. | Correct unit file and revalidate. | Linux Lead | Open | 2026-07-27
R10 | Schedule slips due to unresolved ITQs | 3 | 3 | 9 | Medium | ITQ due dates and twice-weekly review. | Rebaseline with sponsor approval. | Project Manager | Open | 2026-07-27

## Software & Tools
Software, Platforms and Document Tools
Baseline uses existing infrastructure and open-source Linux components.
Category | Product / Tool | Version / Type | License / Cost | Purpose | Owner | Notes
Virtualization | XCP-ng / Xen Orchestra | Existing lab platform | Existing / Open source | Student VM hosting, console and snapshots | Lab Admin | No student access to other VMs.
Operating System | Rocky Linux | 9.x | Open source | Student process-management platform | Lab Admin | One VM per student.
Shell | Bash | OS supplied | Open source | Scripts and process demonstrations | Student | Root commands in training only.
Process Tools | procps-ng / psmisc | Rocky package | Open source | ps, top, pgrep, pstree and related tools | Student | Mandatory prerequisite.
Compiler | GCC | Rocky package | Open source | Compile zombie process demonstration | Student | Remove not required after lab.
Service Manager | systemd | OS supplied | Open source | Service lifecycle and restart policy | Linux Lead | reportsvc least privilege.
Documentation | Microsoft Excel / LibreOffice | Existing | Existing / Open source | CTR, schedule, NCD, ITQ and PMP | Document Controller | Controlled revision naming.
Documentation | Microsoft Word / LibreOffice | Existing | Existing / Open source | FDS and incident report | Document Controller | Export final PDF for review.
Presentation | Microsoft PowerPoint / LibreOffice Impress | Existing | Existing / Open source | Student handover presentation | Student Team | Bank-style business presentation.

## Business Learning Guide
How the Documents Teach Business Project Delivery
Students should understand why each document exists, who uses it and what decision it supports.
Document | Business Question Answered | Primary Owner | When Used | Key Student Learning | Approval / Decision | Typical Failure if Missing | Project Artifact
CTR | What are we delivering, how long will it take, who is needed and what will it cost? | Project Manager | Initiation / bidding | Scope, commercial estimate and assumptions | Sponsor / Customer approval | Scope and cost disputes | CTR workbook
PMP | How will the project be governed and controlled? | Project Manager | Entire lifecycle | Governance, communication, RACI, risk and quality | Project Sponsor | Unclear roles and unmanaged risks | PMP workbook
Master Schedule | When will each activity and deliverable be completed? | Project Manager / Planner | Planning and status reviews | WBS, dependencies, milestones and forecast | Baseline approval | Late delivery is discovered too late | Schedule workbook
NCD | How will the change be implemented, validated and rolled back safely? | Change Manager / Technical Lead | Before and during implementation | Gates, evidence, risk controls and rollback | Go / No-Go | Uncontrolled changes and difficult recovery | NCD runbook
ITQ Register | What information or decision is still missing? | Business Analyst | Discovery and design | Assumption management and ownership | Query closure | Hidden assumptions become defects | ITQ workbook
FDS | How will the approved requirements be implemented and tested? | Linux Technical Lead | Design and acceptance | Traceability from requirement to design and test | Design approval | Different people build different solutions | FDS DOCX/PDF
Validation Evidence | Did the solution actually meet the acceptance criteria? | Test Lead / Student | Testing | Objective evidence and traceability | Technical acceptance | Claims cannot be proven | NCD validation sheet
Incident Report | What happened, why, what was done and how do we prevent recurrence? | Operations / Student | Incident and closure | Business communication and continual improvement | Instructor / Service Owner | Same problem repeats | Incident report
Presentation / Handover | Can the receiving team operate and support the result? | Student Team | Project close | Executive communication and knowledge transfer | Business acceptance | Solution cannot be supported | PowerPoint / handover